## RAISING CONCERNS 1-5
| VALUES AND CULTURE IN THE FIRE AND RESCUE SERVICE REPORT March 2023 CSSLT Oxfordshire Fire and Rescue Service Gap Analysis ACFO Matt Cook https://www.justiceinspectorates.gov.uk/hmicfrs/news/news-feed/staff-report-bullying-harassment-and-discrimination-in-every-fire-and-rescue-service/ | [5 empty] | Recommendations Index Raising Concerns 1-5 Background checks 6-10 Misconduct Handling 11-19 Leadership 20-24 Management, Leadership Training 25-31 Diversity Data 27-31 Improving Diversity 32-33 Code of Ethics 34 FRS National Framework 35
RAISING CONCERNS
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 1
By 1 October 2023, chief fire officers should make sure their services provide a confidential way for staff to raise concerns and that staff are aware of whistleblowing processes | OFRS are introducing Say So from the 7th May 2023 as part of our Cultural Development Framework. | Finalise procurement and contracts, launch Say So, carry out service wide communications, establish reporting lines, complete 50 station based visits in year 1. | People and Organisational Development | 2023-05-07 | 2023-07-01 | On track Launch undertaken and engagement with FBU. Coms and Posters send to station. | G | 3.10.23
Recommendation 2
By 1 October 2023, National Employers, the Local Government Association and the National Fire Chiefs Council should review any current independent arrangements whereby staff can raise concerns outside their FRS. They should then ensure that all FRS staff have access to an independent reporting line that can be used as a confidential way to raise concerns outside their own FRS. | As above | As above | As above | As above | As above | As above | As above
Recommendation 3
By 1 June 2023, chief fire officers should review the support available for those who have raised concerns and take any action needed to make sure these provisions are suitable. | We are already proactive in reviewing concerns raised by staff, a recent example resulted in an independent appreciative enquiry into the culture within a workplace. | Concerns are reviewed by our external HRBP and the introduction of Say So will enhance this process. | As above | As above | As above | As above | As above |  |  |  |  | We have a mature model of reporting in the workplace which is proactive in its approach in reviewing concerns raised by staff, a very recent example resulted in an independent appreciative inquiry into the culture within a workplace. All concerns are reviewed by our external County Council Human Resource Business Partner (HRBP). To further support the current arrangements, and in response to the recommendation, we have introduced a third party confidential reporting company (Say So) that will allow for individuals to report or raise a concern anonymously if they wish. The new external reporting line (Say So) is being embedded into the service with briefings and training being undertaken for all stakeholders. This includes a personal visit from Say So to all teams and departments, including 50 station based visits in the first year as part of our agreement. We are satisfied that these arrangements are robust and will support all staff in raising concerns. These arrangements will be subject to annual review and performance reporting.
Recommendation 4
By 1 June 2023, chief fire officers should assure themselves that updates on how concerns are being handled are shared with those who have raised them. The updates should be given in an accessible way that encourages trust and confidence in the service response. Consideration should be given to creating a professional standards function to handle conduct concerns in service (or from an external service) to have oversight of cases, to make sure they are conducted in a fair and transparent way and to act as a point of contact for all staff involved. | OFRS are introducing Say So from the 7th May 2023 as part of our Cultural Development Framework. | Finalise procurement and contracts, launch Say So, carry out service wide communications, establish reporting lines, complete 50 station based visits in year 1. | People and Organisational Development | 2023-05-07 | 2023-07-01 | On track Launch undertaken and engagement with FBU. Coms and Posters send to station. | G |  |  |  |  | OFRS have introduced an external service to provide a confidential reporting service that can be the independent consultant between an individual raising a concern and the service. The concern is reported to the County Council HRBP, in which a determination will be made about the course of action. This approach ensures confidentiality and provides an element of independent assurance, our HRBP will then determine how best to approach the concern. The HRBP sits outside of our Directorate and reports directly into the CFO ensuring an additional level of independence and oversight. The methods of raising a concern extend to, reporting to a line manager, or the internal Employee Relations and Resourcing Team, via the County Council processes, or via the third party service (Say So).
Recommendation 5
By 1 June 2023, chief fire officers should make sure they provide accessible information for all staff and members of the public on how they can raise concerns and access confidential support (including through external agencies). Chief fire officers should also make sure accessible information is provided on how concerns and allegations will be investigated in a way that ensures confidentiality and is independent of the alleged perpetrator. | OFRS are introducing Say So from the 7th May 2023 as part of our Cultural Development Framework. | Finalise procurement and contracts, launch Say So, carry out service wide communications, establish reporting lines, complete 50 station based visits in year 1. | People and Organisational Development | 2023-05-07 | 2023-07-01 | On track | G |  |  |  |  | OFRS have introduced an external service to provide a confidential reporting service that can be the independent consultant between an individual raising a concern and the service. To ensure that the concerns are dealt with the report is sent to our County Council HRBP to ensure confidentiality, our HRBP will then determine how best to manage the concern via assigning appropriate support to carry out fact finding or investigations. Raising a concern can be via line management, or our internal Employee Relations and Resourcing Team, or via our County Council processes, or via our now establishing third party service. In addition, we have also launched an internal staff engagement programme with our external independent reporting service, which includes social media, keeping you connected (Our staff engagement forum), and through face-to-face team-based visits. For all individuals that raise concerns an update is provided on the investigation in a way that ensures confidentiality for all involved. These are all forming part of our developing ‘Delivering the Future Together (DtFT) Cultural Development Framework’. Members of the public can raise concerns through our County Council complaints team, and these are managed through existing processes. Information on how to raise concerns by staff or members of the public is published on our intranet and external website.

## BACKGROUND CHECKS 6-10
BACKGROUND CHECKS
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 6
By 1 January 2024, the Home Office, working with the Ministry of Justice, should make sure that the Government incorporates fire and rescue authority employees within the Rehabilitation of Offenders Act 1974 (Exceptions) Order 1975 so that they are eligible for the appropriate DBS checks. | Monitoring not OFRS specific. | No
Recommendation 7
By 1 May 2024, the Home Office, working with the fire and rescue sector, should make sure that the Police Act 1997 (Criminal Records) Regulations 2002, or a similar appropriate legislatively enabled solution, makes detailed provisions for fire and rescue services. | Monitoring not OFRS specific. | No
Recommendation 8
By 1 December 2023, the Fire Standards Board, in liaison with the National Fire Chiefs Council, should review the existing relevant standard(s) and underpinning guidance. It should: • clearly state the requirements for background checks undertaken by services; • clarify the minimum requirements (including levels of DBS checks) for all roles, particularly roles where staff have access to vulnerable members of the public; • define the standards required to embed a culture across fire and rescue services that empowers all members of staff and local communities to report concerns; and • be subject to review following any legislative change | Monitoring not OFRS specific. | No
Recommendation 9
By 1 January 2024, chief fire officers should: • immediately review their current background checks arrangements, and make sure that suitable and sufficient background checks are in place to safeguard their staff and communities they serve; and • make sure that appropriate DBS check requests have been submitted for all existing, new staff, and volunteers, according to their roles as identified by the Fire Standards Board. | CSS OFRS currently follow OCC's Criminal Record Checking Policy and Guidance. | Yes, review policy based on Home Office/ NFCC Guidance. | https://intranet.oxfordshire.gov.uk/cms/content/safer-recruitment-and-disclosure-and-barring-service-checks |  |  | The Fire Standards Board and NFCC are yet to confirm a list of roles and what requirements are needed. Functional Managers have been aksed to review DBS Requirements in their area.
Recommendation 10
By 1 September 2023, chief constables should make sure they are appropriately using their Common Law Police Disclosure powers in circumstances involving employees of fire and rescue services | Monitoring not OFRS specific. | No

## MISCONDUCT HANDLING 11-19
MISCONDUCT HANDLING
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 11
By 1 December 2023, the Fire Standards Board, in liaison with the National Fire Chiefs Council, should review the existing relevant standard(s) and supporting guidance to clearly state how services should handle staff disclosures, complaints and grievances. | Monitoring not OFRS specific. | No
Recommendation 12
By 1 March 2024, chief fire officers should provide assurances to HMICFRS that they have implemented the standard on staff disclosure, complaint and grievance handling | Subject to national standard.
Recommendation 13
By 1 December 2023, the Fire Standards Board, in liaison with the National Fire Chiefs Council, should review the existing relevant standard(s) and supporting guidance to clearly state how services should handle misconduct and safeguarding-related allegations and outcomes. These should include requirements to: • conduct and complete investigations, whether or not the staff member under investigation leaves; • consider whether the incident requires immediate dismissal; • provide training for staff who are carrying out investigations; and • ensure the diversity/neutrality of the investigation panel/person. | Monitoring not OFRS specific. | No
Recommendation 14
By 1 March 2024, chief fire officers should provide assurances to HMICFRS that they have implemented the standard on misconduct allegations and outcomes handling. | Subject to national standard.
Recommendation 15
By 1 October 2023, the Home Office should work with the National Fire Chiefs Council and fire and rescue service employers to make sure there is a process to handle misconduct allegations against chief fire officers. The Home Office should immediately notify HMICFRS of any allegations and outcomes that it is aware of. | Monitoring not OFRS specific. | No
Recommendation 16
By 1 October 2023, the National Fire Chiefs Council should develop and manage a national barred list that holds details of staff who have been dismissed for gross misconduct (including staff who have already left services). It should ensure that this list is referred to in all appointment processes to prevent those who are barred from rejoining another service. After the College of Fire and Rescue has been established (see recommendation 25), it should take responsibility for managing the list. | Monitoring not OFRS specific. | No
Recommendation 17
With immediate effect, chief fire officers should notify HMICFRS of any allegations that have the potential to constitute staff gross misconduct that: • involve allegations of a criminal nature that have the potential to affect public confidence in FRSs; • are of a serious nature; or • relate to assistant chief fire officers or those at equivalent or higher grades. | Completed, ref CFO letter to Matt Parr. | [10 empty] | Completed - via CFO letter to Matt Parr. 20th February 2023
Recommendation 18
By 1 August 2023, chief fire officers should provide assurances to HMICFRS that all parties are supported in relation to ongoing investigations. | As above.
Recommendation 19
By 1 July 2023, the Home Office should examine whether any appeal processes for fire and rescue misconduct cases are appropriate. | Monitoring not OFRS specific. | No

## LEADERSHIP 20-24
LEADERSHIP
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 20
By 1 June 2023, chief fire officers should have plans in place to ensure they meet the Fire Standards Board’s leading the service standard and its leading and developing people standard. | We are currently reviewing our leadership development programmes through our development programme refresher proposal. OCC have also launched the new 'Delivering Inspiring Leadership: Essentials for Managers' Programme. | Yes, we are reviewing our leadership programmes to ensure they align to the Leading and Developing People Standard. | People and Organisational Development | 2023-01-04 | 31/03/24 |  | G |  |  |  |  | As a service we have completed the ‘Leading the Service’ and ‘Leading and Developing People’ Fire Standard Implementation Tool. This work will form the development of an action plan to fully align the service to these two fire standards. The SLT have assumed responsibility for leading different aspects of the two named Fire Standards and will report performance against the actions periodically. The County Council has launched a co-created workforce planning strategy, which aligns to the succession management strategy for the Service. This was also developed using the NFCC Talent Management Toolkit, resulting in a comprehensive strategy and workforce plan that is monitored through formal governance. All leadership development programmes have been reviewed to ensure they align to the Leading and Developing People Fire Standard, this is an ongoing workstream that forms the focus for our work. The service has access to and utilises the County Council programmes of 'Delivering Inspiring Leadership: Essentials for Managers’, which all managers will be attending, fulfilling an essential aspect of the development pathways for all leaders.
Recommendation 21
By 1 June 2023, chief fire officers should make sure there is a full, 360-degree feedback process in place for all senior leaders and managers (assistant chief fire officer equivalent and above) in service | All managers are offered an insights profile. Employees also have access to coaching and mentoring via the West Midlands and NFCC Coaching Portal. | Yes, we are currently involved in the NFCC early market research for 360 and will assess our needs in line with OCC's DtFT programme. We will aim to intorduce a 360 for our SMs and above initially. | People and Organisational Development | 2023-01-04 | 31/03/24 |  | G |  |  |  |  | An external provider has been identified and procured which will facilitate 360 degree appraisals for all senior leaders, starting with the three Principal Officers. Since 2018 all Group Managers and department Heads (Grey and Green Book leaders) and above have undertaken Insights Personality Profiling, which has greatly enabled continued team development sessions through the County Council organisational development team. Employees also have access to coaching and mentoring via the West Midlands and NFCC Coaching Portal which has incorporated 360 feedback using ‘Stop, Start, continue’ for those undertaking this coaching support.
Recommendation 22
By 1 September 2023, chief fire officers should make sure there is a full, 360-degree feedback process in place for all other leaders and managers in service. The process should include gathering feedback from a wide range of sources including colleagues and direct reports. | All managers are offered an insights profile. Employees also have access to coaching and mentoring via the West Midlands and NFCC Coaching Portal. | Yes, we are currently involved in the NFCC early market research for 360 and will assess our needs in line with OCC's DtFT programme. We will aim to intorduce a 360 for our SMs and above initially. | People and Organisational Development | 2023-01-04 | 31/03/24 |  | G
Recommendation 23
By 1 June 2023, chief fire officers should seek regular feedback from staff about values, culture, fairness and diversity, with due regard to the leading and developing people standard. They should show how they act on this feedback. | We are currently assessing our OCC Staff Survey, we are also launching Say So, we also commissioned a recent appreciative enquiry at Thame Fire Station. | Yes, as per our cultural development framework, we are currently carrying out market research for a culture assessment (Inclusive Employers and 31-Ten). | CSS SLT | 2023-01-04 | 31/03/24 |  | G |  |  |  |  | We are currently assessing our County Council Staff Engagement Survey. As part of this engagement survey, we have designed ‘listening circles’ to create a dialogue with staff about the survey results and are seeking feedback on what we can ‘stop, start, continue’, this includes feedback from staff about values, culture, fairness and diversity, with due regard to the leading and developing people standard (Ref: Fire Standard Criteria 16, and Engagement Survey ‘Leadership & My Manager’). As part of these listening circles, we have developed an action plan to capture feedback. An example is an action based on feedback to review our staff engagement processes. We have launched a third-party confidential reporting line - Say So in which staff can raise anonymous feedback and concerns about values, culture, fairness, and diversity. We are proactively promoting this service through continued staff engagement. We have commissioned a recent appreciative enquiry at a fire station following concerns that have been raised through our in service reporting lines/processes, this was led by an external to FRS County Council manager to ensure impartiality. Watch visits are taking place with a focus on culture, these are landing well with our staff networks and feedback has been extremely positive. Staff and wider stakeholder consultation has commenced on the new cultural development framework, ‘Delivering the Future Together (DtFT) Cultural Development Framework’.
Recommendation 24
By 1 October 2023, chief fire officers should put plans in place to monitor, including through the gathering and analysis of staff feedback, watch and team cultures and provide prompt remedial action for any issues they identify. | We are currently assessing our OCC Staff Survey, we are also launching Say So, we also commissioned a recent appreciative enquiry at Thame Fire Station. | Yes, as per our cultural development framework, we are currently carrying out market research for a culture assessment (Inclusive Employers and 31-Ten). | CSS SLT | 2023-01-04 | 31/03/24 |  | G

## MANAGEMENT LEADERSHIP TRG 25-26
MANAGEMENT AND LEADERSHIP TRAINING AND DEVELOPMENT
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 25
Recommendation 25 By 1 January 2025, the Government should establish a College of Fire and Rescue, as proposed by the White Paper Reforming our Fire and Rescue Service. There should be no further delay to its implementation | Monitoring not OFRS specific.
Recommendation 26
By 1 October 2023, as a precursor to the development of the College of Fire and Rescue, chief fire officers and the National Fire Chiefs Council should work with the Home Office to consider how they can improve the training and support they offer to staff in management and leadership development. This should include authority members in respect of their assurance leadership roles and should ensure that opportunities are offered fairly across all staff groups. | Monitoring not OFRS specific.

## DIVERSITY DATA 27-31
DIVERSITY DATA
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 27
By 1 June 2023, chief fire officers should make sure their equality impact assessments are fit for purpose and, as a minimum, meet the requirements of the National Fire Chiefs Council equality impact assessment toolkit. | We will need to start a review on this with our HRBP. | Yes | HRPB and People and Organisational Development | 31/03/2023 | 31/03/24 |  | A |  |  |  |  | Equality Impact Assessments have been used in the service for a considerable time. To ensure currency and assurance of their use, we have instigated a review via our Senior Human Resource Assistant (SHRA) and our HRBP. To ensure a more permanent solution, a new post of ‘Cultural Engagement Officer’ will be introduced into the Service, which will assume the role of assurance for EIA’s. We are in the second phase of reviewing the service plans, policies and actions against the NFCC EDI Maturity Assessment Tool to identify and better understand the areas for improvement.
Recommendation 28
By 1 June 2023, chief fire officers should review how they gather and use equality and diversity data to improve their understanding of their staff demographics, including applying and meeting the requirements of the National Fire Chiefs Council equality, diversity and inclusion data toolkit | We will need to start a review on this with our HRBP. | Yes | HRPB and People and Organisational Development | 31/03/2023 | 31/03/24 |  | A |  |  |  |  | A review of data has been instigated via our Senior Human Resource Assistant (SHRA) and HRBP. The introduction of a new ‘Cultural Engagement Officer’ will ensure the service is in a good position to understand how the service gathers and uses equality and diversity data to improve our understanding of our staff demographics, including applying and meeting the requirements of the National Fire Chiefs Council equality, diversity and inclusion data toolkit. The service has completed the NFCC EDI Maturity Assessment to review and develop understanding areas for improvement.
Recommendation 29
By 1 December 2023, the Home Office should publish greater detail on the protected characteristic data it collects about FRS staff, including joiners and leavers, by rank and role. | Monitoring not OFRS specific. | No
Recommendation 30
By 30 December 2024, the Home Office should align the data it collects on protected characteristics with the Office for National Statistics harmonised standard and publish this data | Monitoring not OFRS specific. | No
Recommendation 31
By 1 December 2024, the Home Office should collect and publish experimental statistics on public complaints and conduct matters in relation to FRS staff, similar to that which it currently publishes on police forces in England and Wales. | Monitoring not OFRS specific. | No

## IMPROVING DIVERSITY 32-33
IMPROVING DIVERSITY
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 32
By 1 June 2023, chief fire officers should, as a priority, specify in succession plans how they intend to improve diversity across all levels of the service. This should include offering increased direct-entry opportunities. | We have completed the NFCC EDI Maturity Model and will use this to improve our new OCC Workforce Plan, Succession Management Plan, and we are part of the national cohort for Direct Entry. | Yes ongoing | People and Corporate Services | 2023-04-01 | 2024-04-01 | We are one of 7 participating FRS in the national Direct Entry Programme. | G |  |  |  |  | We have completed the NFCC EDI Maturity Model along with running an EDI Maturity Model event via NFCC and have a further session planned for July 2023. We have undertaken a County Council Workforce Plan, and have developed our Succession Management Strategy, which will link into our promotional policies and procedures. This strategy is in line with the NFCC Talent Management Toolkit. We are part of the NFCC national cohort for Direct Entry, working closely with the NFCC team. We are nearing the point of selection of a direct entry Station Manager into our service. We undertake regular have a go day’s and encourage diverse community members to attend via communication means available to us. We are preparing for Wholetime recruitment for early 2024 where we will aim to have a diverse cohort. We undertake regular direct transfers from our On Call to Wholetime duty systems. We are opening up our next Area Manager post to both grey and green book to encourage diversity at this strategic level. Our SLT is made up of Gold, Grey and Green book staff members ensuring the diversity at the strategic level.
Recommendation 33
By 1 August 2023, chief fire officers should develop plans to promote progression paths for existing staff in non-operational roles and put plans in place to reduce any inequalities of opportunity | We have completed the NFCC EDI Maturity Model and will use this to improve our new OCC Workforce Plan, Succession Management Plan, and we are part of the national cohort for Direct Entry. | Yes ongoing | People and Corporate Services | 2023-04-01 | 2024-04-01 |  | G

## CODE OF ETHICS 34
CORE CODE OF ETHICS
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 4
With immediate effect, chief fire officers should review their implementation of the Core Code of Ethics and make sure it is being applied across their services. | We are using the CCoE in our selection processes and will assess its use in our leadership development work. | Yes, we are looking to integrate the CCoE into our leadership development programmes. | People and Organisational Development | 2023-04-01 | 2024-04-01 |  | G |  |  |  |  | We are integrating the principles of the Core Code of Ethics into all leadership development programmes, linking closely with our County Council Values and Behaviours framework. We have completed the CCoE Fire Standard Implementation Tool and completed a gap analysis to confirm that our Service’s Vision, Purpose, and Values fully align to the CCoE, these are applied across the service.

## F&R NATIONAL FRAMEWORK 35
The Fire and Rescue National Framework for England
Recommendations | Current Position | Action Required? | Responsible Person and Function/Team | Expected start date | Expected end date | Comments | RAG | Date Closed | 2023-04-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
Recommendation 35
By the end of this Parliament, the Government should consider the findings and recommendations in this report when refreshing the Fire and Rescue National Framework for England | Monitoring not OFRS specific.